## Dashboard
StageForge / UPP Rebuilt Master Backlog
Checkpoint 74 baseline · Native Windows/CoreAudio device monitor lifecycle passed hosted CI · 25 items remain open
TOTAL OPEN | P0 | READY | BLOCKED | DEFERRED | SOFTWARE | QUALIFICATION | DECISIONS
25 | 22 | 0 | 11 | 7 | 4 | 19 | 2
Phase | Open Items | Intent |  | Order | Next slice | Exit condition | Primary gate
5.2 | 0 | Finish explicit audio conversion execution |  | 1 | Independent-witness multi-host drill | Separate witness hosts/power/network prove 2/3 survival, 1/3 denial, clock bounds and fenced-node recovery | Actual independent hosts
5.3 | 6 | Security, packaging, browser acceptance |  | 2 | Venue/control LAN + browser-network qualification | Real TLS certificate, reverse proxy, IdP, firewall and browser/session path behave under controller load | Deployed network
5.4 | 0 | DAW durability, authority, public-record groundwork |  | 3 | Clean-host Linux packaging qualification | Install/reinstall/uninstall plus service/device permissions match the package contract | Fresh Linux host/VM with devices
5.5 | 7 | Windows/macOS, plugin and IPC coverage |  | 4 | Windows/macOS audio + device lifecycle implementation | Physical audio negotiation and persistent hotplug/recovery semantics reach parity with Linux | Platform implementations + CI
6.0 | 11 | Named-hardware and production qualification |  | 5 | Native device events and stream integration | Deliver native events to the reconciler; prove safe stream loss/recovery | Target-OS integration evidence
6.x | 1 | Longer-horizon governance and RF expansion |  | 6 | AT/plugins/named-hardware qualification | Accessibility, licensed plugin and stage support claims are measured on actual platforms/hardware | External qualification environments
Operating rule
Never convert software evidence into a hardware/stage-support claim. Discovery, simulation, protocol conformance, and unit tests can close software work, but named hardware, timing, RF, audible behavior, and failover still require qualification evidence.
Source of truth
GitHub main f2fd64952c61f737e8b3dc60ee0afe86cd7de965 is canonical. Checkpoint 73 PLUG-034 remains Done; licensed compatibility remains PLUG-035/036. Checkpoint 74 adds native enumeration and listener stop/restart evidence on Windows/macOS. DEV-033/034 remain In Progress: event delivery, persistent identity, MIDI and engine integration are still open. Streaming and physical hardware are not qualified.

## Backlog
ID | Workstream | Layer | Work Item | Outcome | Priority | Status | Phase | Type | Dependency / Prerequisite | Acceptance Criteria | Verification | Risk | Source | Rank Score
REC-033 | Recovery / Redundancy | Operations | Multi-host persistently-fenced-node recovery drill | Prove the completed recovery protocol across genuinely separate hosts without restoring authority or arming outputs | P0 | Blocked | 6.0 | Qualification | WIT-048 | Recovery receipt precedes fence removal; recovered node remains standby/disarmed across a real multi-host drill with one witness unavailable | Independent multi-host drill with witness, clock and output-state evidence | Critical | docs/current-backlog.md priority 1 | 430
REC-034 | Recovery / Redundancy | Operations | Physical independent-witness recovery qualification | Validate recovery/fencing against witnesses deployed in genuinely separate failure domains | P0 | Blocked | 6.0 | Qualification | REC-033, WIT-048 | No StageForge node, shared host, shared power/network failure domain or single witness can unilaterally authorize recovery | Independent witness host/network/power failure-domain exercise | Critical | docs/current-backlog.md priority 1 | 430
SEC-033 | Security | Deployment | Proxy-HTTPS deployment contract + qualification tooling | Make the reviewed TLS/auth reverse-proxy boundary machine-checkable while keeping the StageForge backend loopback-only | P0 | Done | 5.3 | Software | Astra 22-32 hardening | Strict profile rejects unsafe deployment configuration; backend and TLS-edge probes verify the documented contract | 6 deployment tests + live local TLS reference exercise + installer packaging checks | Critical | docs/astra-checkpoint-33-validation.md | 0
SEC-034 | Security | Backend | Authorization-audit retention and rotation | Bound durable actor/action audit storage without breaking chain verification | P0 | Done | 5.3 | Software | SEC-033 | Rotation is atomic, bounded and continuous; pruning commits a cryptographic retention anchor before deletion | 5 retention/rotation durability tests including tamper, ENOSPC and crash residue | Critical | docs/astra-checkpoint-34-validation.md | 0
SEC-035 | Security | Backend | Specialized authorization-audit unification | Unify durable evidence for admin-token, adapter-report and selected machine-HMAC authorization without widening human roles | P1 | Done | 5.3 | Software | SEC-034 | Specialized allow/deny decisions are persisted before execution; machine HMAC evidence is emitted after verification and before mutation; credentials/raw payloads are excluded | 6 new specialized authorization regressions; 506-test release suite; 2/2 native CTest; 117 schemas/OpenAPI; 7 JS syntax checks | High | docs/astra-checkpoint-36-validation.md | 0
SEC-036 | Security | Replication | Witness/replication HMAC key lifecycle and rotation | Rotate cluster authentication keys without restart, split-brain, silent downgrade, or changing authority semantics | P0 | Done | 5.3 | Software | SEC-033 | Old/new overlap is explicit; outbound traffic names the active key; removed keys fail closed; witness quorum operations pin one immutable snapshot | 8 rotation regressions + live witness rotation + 500-test release suite + 2/2 CTest | Critical | docs/astra-checkpoint-35-validation.md | 0
SEC-037 | Security | Performance | Controller workload and rate-policy qualification | Qualify representative controller HTTP bursts separately from abusive-rate containment without claiming physical controller timing | P0 | Done | 5.3 | Qualification | SEC-033, SEC-038 | Deterministic rate model admits representative controller workload beside an abusive peer; live local reference meets normal p95 gate and produces explicit throttling under abuse | 400/400 model controller requests admitted; 802 abusive rejected; live 120/120 normal at 22.903 ms p95; 33/320 abuse requests throttled | Critical | docs/astra-checkpoint-38-validation.md | 0
SEC-038 | Security | Backend | Backend operation-cost bounds | Prevent known expensive authenticated operations from exhausting the HTTP worker pool or starving ordinary control traffic | P0 | Done | 5.3 | Software | SEC-033 | Known expensive routes have explicit non-blocking total/class admission budgets; saturation rejects before body execution and slots are reclaimed on failure | 4 operation-cost regressions; 510-test release suite; 2/2 native CTest; 117 schemas/OpenAPI; 7 JS syntax checks | Critical | docs/astra-checkpoint-37-validation.md | 0
SEC-039 | Security | Witness | Independent witness clock/failure-domain deployment qualification | Measure the real clock, network and failure-domain assumptions that still gate production quorum/failover confidence | P0 | Blocked | 5.3 | Qualification | WIT-048, REC-034 | Actual witness hosts maintain the accepted skew bound and survive declared single-domain failures without manufacturing two authorities | Real multi-host skew, partition, one-/two-witness-loss and custody/rotation exercise | Critical | docs/current-backlog.md priority 2 | 430
DAW-033 | DAW | Storage | Power-loss recovery for temporary resources | Make crash-visible staging, snapshots and plugin scratch conservatively recoverable without deleting replacement objects | P1 | Done | 5.4 | Software | Completed temporary-resource lifecycle | Versioned fsynced owner manifests bind exact process generation to device/inode identity; legacy/malformed/replaced objects are preserved and cleanup rechecks identity before deletion | 38 focused durability tests; 524-test release suite; 2/2 RT CTest; 117 schemas/OpenAPI; 7 JS syntax checks | High | docs/astra-checkpoint-40-validation.md | 0
DAW-034 | DAW | Storage | Parent-directory durability for published recordings | Raise recording publication from file-sync durability to explicit parent-directory durability on Linux | P1 | Done | 5.4 | Software | DAW-033 | Completed WAV bytes are fsynced; non-replacing hard-link publication and partial cleanup each have explicit parent-directory sync ordering with retry-safe failure behavior | 20 focused recording tests; 527-test release suite; 2/2 RT CTest; 117 schemas/OpenAPI; 7 JS syntax checks | High | docs/astra-checkpoint-41-validation.md | 0
DAW-035 | DAW | Playback | Sample-exact loop wraps and arbitrary loop lengths | Allow any positive arrangement/clip loop span while preserving exact software wrap position through fixed-size producer/native blocks | P1 | Done | 5.4 | Software | DAW playback producer + native queue | Producer wraps exact source slices inside a block without silence padding; clip loops keep exact length; native playhead advances modulo the exact span and counts multiple wraps | 529-test release suite; 2/2 RT CTest; focused 3-frame/8-frame, 257-frame clip and live 300-frame loop regressions | High | docs/astra-checkpoint-42-validation.md | 0
AUD-033 | Audio | Native | Linux integer + multichannel physical PCM conversion adapters | Execute explicit Linux ALSA integer-format and channel-layout plans on the live playback/capture path | P0 | Done | 5.2 | Software | Linux audio negotiation contract | FLOAT_LE, S16_LE, S24_3LE and S32_LE plus explicit mono/multichannel matrices execute with preallocated bounded conversion and no silent fallback | 516-test release suite; 2/2 RT native CTest; live ALSA-null 4ch S16 playback + 4ch S24_3LE capture | Critical | docs/astra-checkpoint-39-validation.md | 0
AUD-034 | Audio | QA | Conversion quality measurement | Quantify noise, distortion, phase continuity and resampling quality across supported conversions | P0 | Blocked | 6.0 | Qualification | AUD-033 | Published numeric error/SNR/THD+N/continuity envelope for each supported conversion path | Reference-signal measurement suite | Critical | docs/current-backlog.md priority 4 | 430
AUD-035 | Audio | Platform | Windows exact audio preflight/configuration + stream adapter | Implement WASAPI endpoint capability/configuration evidence and physical stream open/close using checkpoint-58 backend-neutral fencing | P0 | In Progress | 5.5 | Software | AUD-033, Checkpoint 58 runtime fencing | Windows adapter reports requested/configured rate/period/channels/format exactly, applies only explicit conversion plans, and uses shared post-start identity revalidation/stop-on-loss | Windows CI + named interface fixtures + live WASAPI run | Critical | docs/current-backlog.md priority 4 | 480
AUD-036 | Audio | Platform | macOS exact audio preflight/configuration + stream adapter | Implement CoreAudio capability/configuration evidence and physical stream open/close using checkpoint-58 backend-neutral fencing | P0 | In Progress | 5.5 | Software | AUD-033, Checkpoint 58 runtime fencing | CoreAudio adapter reports requested/configured rate/buffer/channels/format exactly, applies only explicit conversion plans, and uses shared post-start identity revalidation/stop-on-loss | macOS CI + named interface fixtures + live CoreAudio run | Critical | docs/current-backlog.md priority 4 | 480
DEV-033 | Devices | Platform | Windows audio/MIDI enumeration + hotplug integration | Feed real Windows endpoint/MIDI enumeration and change notifications into the checkpoint-57 fail-closed lifecycle reconciler | P0 | In Progress | 5.5 | Software | Checkpoint 57 lifecycle reconciler (not present in GitHub module repository); Checkpoint 74 native device monitor | Windows platform adapters provide persistence-grade identities where available; disconnect/identity change stops unsafe streams, ambiguity blocks rebind, and strong identity may reattach only to one exact replacement | Checkpoint 74 hosted Windows MMDevice: 0 devices, no defaults; 25 listener stop/restart cycles in 0.304136s; inactive-snapshot and wrong-thread rejection; active destruction passed. No notification event observed. Remaining: event delivery, persistent identities, MIDI, engine integration and stream loss/reselection tests. | Critical | PR #6; main f2fd64952c61f737e8b3dc60ee0afe86cd7de965; https://github.com/colinatwood/stageforge/actions/runs/34872231466 | 480
DEV-034 | Devices | Platform | macOS audio/MIDI enumeration + hotplug integration | Feed real CoreAudio/CoreMIDI enumeration and change notifications into the checkpoint-57 fail-closed lifecycle reconciler | P0 | In Progress | 5.5 | Software | Checkpoint 57 lifecycle reconciler (not present in GitHub module repository); Checkpoint 74 native device monitor | CoreAudio/CoreMIDI adapters provide hashed persistent identities; disconnect/identity change stops unsafe streams, ambiguity blocks rebind, and recovery remains explicit when evidence weakens | Checkpoint 74 hosted macOS CoreAudio HAL: 3 devices, input/output defaults present; 25 listener stop/restart cycles in 0.25571s; inactive-snapshot and wrong-thread rejection; active destruction passed. No notification event observed. Remaining: event delivery, persistent identities, MIDI, engine integration and stream loss/reselection tests. | Critical | PR #6; main f2fd64952c61f737e8b3dc60ee0afe86cd7de965; https://github.com/colinatwood/stageforge/actions/runs/34872231466 | 480
DEV-035 | Devices | QA | Physical hotplug qualification | Measure repeated unplug/replug/re-enumeration behavior on named devices | P0 | Deferred | 6.0 | Qualification | DEV-033, DEV-034 | No crash, stale authority, accidental re-arm or identity confusion across repeated device churn | Named-device hotplug soak | Critical | docs/current-backlog.md priority 5 | 420
DRV-033 | Driver Compatibility | Data | Reviewed vendor driver catalog entries | Maintain a small provenance-bearing package-metadata catalog with proactive expiry auditing, without turning package records into compatibility or qualification claims | P1 | Done | 5.3 | Software | Existing exact catalog matching | Current exact entries carry product/version/platform/review-expiry/confidence and multi-source evidence; offline audit surfaces due/stale/unreviewed/invalid records before expiry | Five reviewed Windows records; 10/10 driver catalog/audit tests; 572-test release suite; installed audit CLI | Medium | docs/astra-checkpoint-53-validation.md | 0
DRV-034 | Driver Compatibility | Platform | Windows endpoint/driver evidence adapter | Map Windows AudioEndpoint presence and installed signed MEDIA-driver identity into the diagnostics model without exposing full instance identifiers | P1 | Done | 5.5 | Software | DRV-033 | Endpoint hashes, safe VID/PID and installed provider/version/INF/signature evidence remain distinct from reviewed package metadata and never authorize installation | Fixed read-only PowerShell adapter + privacy/failure-isolation fixtures; real Windows host execution remains qualification | High | docs/astra-checkpoint-55-validation.md | 0
DRV-035 | Driver Compatibility | Platform | macOS endpoint/driver evidence adapter | Represent CoreAudio device evidence in the diagnostics model without inventing Windows-style package semantics | P1 | Done | 5.5 | Software | DRV-033 | CoreAudio device UID material is hashed; manufacturer/transport/channel hints are normalized when present; package/INF/version claims remain absent | system_profiler SPAudioDataType fixture/integration coverage; real macOS host execution remains qualification | High | docs/astra-checkpoint-55-validation.md | 0
LIVE-033 | Live Audio | QA | Physical/audible streaming-voice soak | Validate the 16-voice streaming engine under real storage/audio timing | P0 | Deferred | 6.0 | Qualification | Software streaming voice engine complete | No callback I/O, bounded starvation evidence, acceptable audible behavior and sustained xrun envelope | Long-duration named-hardware soak | Critical | docs/current-backlog.md priority 7 | 420
PLUG-033 | Plugins | QA | Real-plugin live-audio qualification | Exercise isolated plugin lifecycle, delay compensation and recovery with licensed fixtures | P0 | Blocked | 6.0 | Qualification | Plugin host lifecycle + delay graph | Known plugins fail, recover and align within documented timing/latency bounds without unsafe auto-rearm | Licensed VST3/CLAP/LV2/AU matrix | Critical | docs/current-backlog.md priorities 3,7,10 | 430
UX-033 | Browser UX | Frontend | Rendered operator workflow acceptance | Verify the production operator assets through a real Chromium renderer beyond static DOM and handler contracts | P1 | Done | 5.3 | Qualification | Served contract hardened | Stage launcher, keyboard bypass, player selection and a safe show-state edit render and execute without browser console/page errors | Real Chromium qualification with production HTML/CSS/JS and real-handler API bridge | High | docs/astra-checkpoint-54-validation.md | 0
UX-034 | Browser UX | Frontend | Responsive visual review | Qualify layout and interaction across practical desktop/tablet/phone reference widths | P1 | Done | 5.3 | Qualification | UX-033 | 1440×900, 1024×768, 768×1024 and 390×844 render with zero document-level horizontal overflow and visible stage controls | Chromium screenshots + automated overflow/visibility checks | Medium | docs/astra-checkpoint-54-validation.md | 0
UX-035 | Browser UX | Accessibility | Assistive-technology exercise | Exercise the checkpoint-62 browser semantics with actual screen-reader/keyboard operator workflows and decide switch/voice-control scope | P1 | In Progress | 5.3 | Qualification | UX-033, UX-034, Checkpoint 62 AX-tree reference | Stage-critical workflows are operable with keyboard and at least one selected screen-reader stack without status loss; any switch/voice requirements are explicitly accepted or deferred | NVDA/VoiceOver or equivalent AT exercise with issue log and operator workflow evidence | High | docs/current-backlog.md priority 8 | 170
PKG-033 | Packaging | Linux | Clean-host install / upgrade / uninstall exercise | Move checkpoint-61 isolated-rootfs reference evidence onto a genuinely clean Linux host/VM and boot the packaged services | P0 | In Progress | 5.3 | Qualification | Checkpoint 61 isolated-rootfs qualifier | Fresh host install, reinstall, state preservation, service startup/health, uninstall and purge match the documented contract without hidden source-tree dependencies | Clean VM/host exercise using the installed package qualifier plus actual service boot | Critical | docs/current-backlog.md priority 9 | 480
PKG-034 | Packaging | Linux | Service permission + hardware namespace qualification | Run the checkpoint-68 installed service-identity permission verifier against the exact ALSA/MIDI/UWB nodes on a clean deployment host | P0 | In Progress | 5.3 | Qualification | PKG-033, Checkpoint 68 device-permission verifier | The stageforge service identity has only the documented read/write access to required character-device nodes; symlink/non-device paths fail closed and no installer step broadens host permissions automatically | Clean-host run as stageforge using stageforge-device-permissions.py plus service/udev/group evidence | Critical | docs/astra-checkpoint-68-validation.md | 480
LEGAL-001 | Release | Governance | Choose and publish project license | Remove the explicit release blocker around redistribution terms | P0 | Blocked | 5.3 | Decision | Owner decision | Repository and packaged notices state one approved license consistently | Owner approval + release-check validation | Critical | docs/current-backlog.md priority 9 | 430
PLUG-034 | Plugins | Security | Windows/macOS native plugin verification-to-launch binder | Bind verified executable identity to process launch on Windows and macOS without a path-digest fallback | P0 | Done | 5.5 | Software | Checkpoint 73 hosted Windows/macOS native-launch evidence | Windows holds the verified executable against replacement through SHA-256 + Authenticode + file-identity launch; macOS launches a private exact-byte staged copy verified by codesign/CDHash and enforces configured signing identity requirements; no path-only fallback | Hosted Windows/macOS native-launch smoke with signed OS fixtures passed. macOS system fixture had no Team ID, so Team-ID matching was not exercised. Licensed product matrix remains PLUG-035/036. | Critical | GitHub main f18b0da1a5ce429dc42bed759ce4154668f021c7 | 0
PLUG-035 | Plugins | Platform | Windows real adapter runs | Prove supported plugin formats and host isolation on Windows | P0 | Blocked | 5.5 | Qualification | PLUG-034 | Selected real plugins pass load/control/audio/restart/failure matrix on Windows | Licensed Windows plugin matrix | Critical | docs/current-backlog.md priority 10 | 430
PLUG-036 | Plugins | Platform | macOS real adapter runs | Prove supported plugin formats and host isolation on macOS | P0 | Blocked | 5.5 | Qualification | PLUG-034 | Selected real plugins pass load/control/audio/restart/failure matrix on macOS | Licensed macOS plugin matrix | Critical | docs/current-backlog.md priority 10 | 430
PLUG-037 | Plugins | QA | Licensed plugin fixture set | Create a legally usable conformance/compatibility fixture inventory | P0 | Blocked | 5.5 | Decision | LEGAL-001 | Fixture licenses permit automated qualification and redistribution rules are documented | Fixture inventory review | High | docs/current-backlog.md priority 10 | 420
PLUG-038 | Plugins | QA | Real product compatibility matrix | Publish evidence-backed compatibility instead of generic format claims | P1 | Blocked | 6.0 | Qualification | PLUG-035, PLUG-036, PLUG-037 | Matrix records exact product/version/OS/arch/results and separates tested from untested | Repeatable compatibility runs | High | docs/current-backlog.md priority 10 | 120
IPC-033 | Local IPC | Platform | Windows UPPF named-pipe DACL + SCM lifecycle | Provide protected explicit-SID named-pipe transport with live DACL attestation, unauthorized-client denial and bounded production-style SCM lifecycle | P0 | Done | 5.5 | Software | Checkpoint 72 hosted Windows evidence | Protected DACL exactly matches configured principals; authorized authenticated UPPF succeeds; excluded client is denied; LocalSystem service stops/restarts both after traffic and while idle in pending accept without stale handles | GitHub Windows Server 2025 hosted kernel/SCM evidence, including idle STOP 0.266s and post-restart authenticated roundtrip | Critical | GitHub main 520a7648fb48a83ca479441b3e4febc3a662115a | 0
LIGHT-033 | Lighting | Native / Venue | sACN + semantic fixture/venue-patch mapping | Move portable lighting intent above raw universe/channel execution while preserving explicit physical-output authority | P1 | Done | 5.5 | Software | Existing lighting scheduler + venue patch | Explicitly armed unicast Art-Net/sACN execution is protocol-selectable; committed venue fixtures resolve semantic parameters deterministically to bounded DMX coordinates | 533-test release suite; 2/2 RT CTest; E1.31 packet/arm vectors; committed venue semantic API integration; 118 schemas/OpenAPI; 7 JS checks | High | docs/astra-checkpoint-44-validation.md | 0
AUTH-040 | Authority | Core / Backend | Department/resource authority leases | Generalize explicit temporary authority beyond current venue-patch scopes without weakening cluster or API authorization | P1 | Done | 5.4 | Software | Venue authority lease foundation | Typed patch/department/resource scopes, exact-resource precedence, venue/runtime lifecycle separation, expiry/audit and fail-closed authority-loss cleanup are explicit | 540-test release suite; 15 focused authority/reconciliation tests; 2/2 RT CTest; 118 schemas/OpenAPI; 7 JS syntax checks | High | docs/astra-checkpoint-45-validation.md | 0
REC-035 | Public Record | Backend | Signed adaptation receipts + externally witnessed Public Record | Make adaptation and operational-authority evidence tamper-evident and independently witnessable outside private show state | P1 | Done | 5.4 | Software | AUTH-040 | Append-only signed records carry stable receipt references; separately authenticated external witnesses attest exact record hashes with explicit quorum coverage | 545-test release suite; tamper/witness/receipt regressions; 2/2 RT CTest; 120 schemas/OpenAPI; 7 JS syntax checks | High | docs/astra-checkpoint-46-validation.md | 0
GOV-033 | Governance | Backend | Bind technology maturity evidence to signed conformance receipts | Replace self-declared interoperability maturity evidence with verifiable signed Public Record receipts | P2 | Done | 6.x | Software | REC-035 | Standard recognition requires an exact verified evidence digest; stale/fake receipts fail and Core elevation requires current-scale eligibility | 548-test release suite; receipt/tamper/stale/current-scale regressions; 2/2 RT CTest; 121 schemas/OpenAPI; 7 JS checks | Medium | docs/astra-checkpoint-47-validation.md | 0
GOV-034 | Governance | Backend | Bind community governance events to Public Record | Make proposal/version/invitation/ballot/ratification history independently auditable without exposing voter identity or individual choice | P2 | Done | 6.x | Software | REC-035 | Current proposal versions, invitation windows and opaque ballot commitments enter the signed Public Record; adoption exposes only aggregates and exact evidence references; missing evidence blocks binding until reconciliation | 559-test release suite; 18 focused governance tests; 2/2 RT CTest; 124 schemas/OpenAPI; 7 JS syntax checks | Medium | docs/astra-checkpoint-49-validation.md | 0
AUTH-041 | Identity | Backend | Real account-auth adapter for community voting | Replace production dependence on forwarded email magic-link credentials with bounded sessions minted from the trusted authentication-proxy identity | P1 | Done | 5.5 | Software | GOV-034 | Active community accounts receive short-lived signed sessions bound to persisted auth generation; revoked/stale sessions fail before mutation and session voting still requires exactly one active current-version invitation | 566-test release suite; trusted-proxy HTTP session issue/vote/revoke regression; 2/2 RT CTest; 125 schemas/OpenAPI; 7 JS syntax checks | High | docs/astra-checkpoint-50-validation.md | 0
HW-033 | Stage Qualification | Audio | Audio latency/dropout/soak qualification | Establish stage-qualified latency/xrun/soak envelope on named hardware | P0 | Deferred | 6.0 | Qualification | AUD-033, AUD-034 | Published named-hardware limits include p95/p99 callback timing, xruns and sustained runtime | Qualification harness | Critical | docs/current-backlog.md deferred equipment | 420
HW-034 | Stage Qualification | Recording | Physical recording + audible loop correctness | Validate live capture, publication and loop playback acoustically/physically | P0 | Deferred | 6.0 | Qualification | DAW-034, DAW-035 | No unexplained discontinuity/corruption across defined capture and loop scenarios | Physical loopback + listening/measurement suite | Critical | docs/current-backlog.md deferred equipment | 420
HW-035 | Stage Qualification | Controllers | Controller timing + reconnect measurement | Measure end-to-end mapped-control timing and reconnect behavior | P0 | Deferred | 6.0 | Qualification | DEV-033, DEV-034, SEC-037 | Published event-to-action latency/jitter and reconnect envelope on named controllers | Controller qualification harness | Critical | docs/current-backlog.md deferred equipment | 420
HW-036 | Stage Qualification | RF | LE Audio / UWB RF + clock validation | Validate wireless timing/RF behavior rather than treating discovery as support | P1 | Deferred | 6.x | Qualification | Named LE/UWB hardware | Published RF, clock, loss and recovery evidence under defined venue conditions | RF/clock qualification harness | High | docs/current-backlog.md deferred equipment | 110
HW-037 | Stage Qualification | Redundancy | Independent multi-host timing + failover measurement | Measure actual failover/program gap across independent nodes | P0 | Deferred | 6.0 | Qualification | REC-033, REC-034 | Published authority and audible/program continuity envelope with independent clocks/hosts | Two-node rehearsal + witness capture | Critical | docs/current-backlog.md deferred equipment | 420
SEC-040 | Security | Deployment | Real LAN TLS/proxy/IdP/firewall qualification | Exercise the checkpoint-33 contract on the actual deployment topology rather than a local reference proxy | P0 | Blocked | 5.3 | Qualification | SEC-033, WIT-048, SEC-039 | Production proxy certificate, human identity injection, firewall/ingress policy and backend denial behavior all match the reviewed contract under controller workload | Deployed qualification report with failure injection and controller traffic | Critical | docs/current-backlog.md priority 2 | 430
WIT-048 | Recovery / Redundancy | Witness | Strict independent-witness deployment topology | Make quorum require distinct configured witness identities, failure domains, per-endpoint credentials and bounded clock assumptions | P0 | Done | 5.3 | Software | SEC-036 | Explicit majority topology; unique IDs/domains/keyrings; HTTPS outside loopback; signed identity/domain/clock fencing; one-witness loss tolerated and two-witness loss denied | 555-test release suite; 71 focused tests; 3-process 3/3→2/3→1/3 drill; 2/2 RT CTest; 123 schemas/OpenAPI | Critical | docs/astra-checkpoint-48-validation.md | 0

## Completed Checkpoints
Checkpoint | Delivered | Tests Passed | Suite | Native Evidence | Remaining Seam | Date
22 | Strict HTTP request framing + body isolation | 427 | Python | No fresh native build | Proxy/TLS trust, resource bounds, auth review | 2026-09-13
23 | Bounded HTTP workers + inactivity timeout | 431 | Python | No fresh native build | Total deadlines, SSE budget, rate limits | 2026-09-13
24 | Separate SSE admission budget | 434 | Python | No fresh native build | Rate limits, proxy/TLS, authorization | 2026-09-13
25 | Monotonic total request receive deadline | 436 | Python | No fresh native build | Rate limits, proxy/TLS, secret lifecycle | 2026-09-13
26 | Per-peer + aggregate request-rate buckets | 440 | Python | No fresh native build | Workload qualification, operation-cost bounds | 2026-09-13
27 | Proxy privilege separation + header/log hardening | 450 | Python | No fresh native build | Deployment TLS, roles, secret rotation, audit | 2026-09-13
28 | Authenticated health + strict command identity | 455 | Python | No fresh native build | Security priority 2 consolidation | 2026-09-13
29 | Scoped monitoring credential | 460 | Python | No fresh native build | Per-user roles, secret lifecycle, durable audit | 2026-09-13
30 | Private credential-file rotation | 467 | Python | No fresh native build | In-flight/SSE revocation; witness/replication rotation | 2026-09-13
31 | SSE file-backed revocation checks | 470 | Python | No fresh native build | Per-user roles + durable actor/action audit | 2026-09-13
32 | Per-user roles + durable hash-linked authorization audit | 481 | Python + CTest | 2/2 native CTest | TLS/proxy qualification, audit retention, secret lifecycle | 2026-09-13
33 | Strict proxy-HTTPS deployment profile + qualification harness | 487 | Python + live local TLS reference | 2/2 native CTest | Real LAN proxy/cert/IdP/firewall qualification | 2026-09-13
34 | Bounded segmented authorization-audit retention + cryptographic prune anchor | 492 | Python + clean RT gate | 2/2 RT CTest | Specialized auth audit unification; controller/disk qualification | 2026-09-13
35 | Rotating replication/witness HMAC keyrings with exact key IDs and no downgrade fallback | 500 | Release Python + schema/frontend/performance checks | 2/2 native CTest | Specialized auth audit unification; witness clock/trust and real-LAN qualification | 2026-09-13
36 | Specialized admin/adapter/machine authorization audit evidence without privilege widening | 506 | Release Python + schema/frontend/performance checks | 2/2 RT native CTest | Backend operation-cost bounds; controller and deployed LAN/witness qualification | 2026-09-13
37 | Non-blocking total/class admission budgets for known expensive HTTP operations | 510 | Release Python + schema/frontend/performance checks | 2/2 RT native CTest | Controller workload/rate-policy; real LAN and witness qualification | 2026-09-13
38 | Repeatable controller HTTP workload + rate-policy reference qualification | 513 | Release Python + workload/schema/frontend/performance checks | 2/2 RT native CTest | Physical controller timing; real LAN and independent witness qualification | 2026-09-13
39 | Linux integer/multichannel physical PCM adapters with explicit conversion-policy fencing | 516 | Release Python + schema/frontend/performance checks | 2/2 RT native CTest + live ALSA-null S16/S24 4ch | Converter-quality measurement; Windows/macOS physical audio adapters | 2026-09-13
40 | Durable inode-bound temporary-resource owner manifests with conservative crash cleanup | 524 | Release Python + durability/schema/frontend/performance checks | 2/2 RT native CTest | Recording publication directory durability; physical storage power-cut qualification | 2026-09-13
41 | Parent-directory durability for finalized and recovered recording publication | 527 | Release Python + recording/schema/frontend/performance checks | 2/2 RT native CTest | Physical storage power-cut/audible capture qualification; arbitrary loop-wrap completion | 2026-09-13
42 | Sample-exact arbitrary-length arrangement/clip loop wrapping across producer and native queue | 529 | Release Python + automation/schema/frontend checks | 2/2 RT native CTest | Audible real-output loop qualification; cross-platform adapters | 2026-09-13
43 | Reviewed, expiring multi-source driver package metadata with stale/unreviewed fencing | 531 | Release Python + driver/schema/frontend/performance checks | 2/2 RT native CTest | Windows/macOS endpoint evidence adapters; broader vendor review and physical qualification | 2026-09-13
44 | Explicit unicast sACN/E1.31 plus semantic fixture resolution through committed venue patches | 533 | Release Python + lighting/schema/frontend/performance checks | 2/2 RT native CTest | Real console/network interoperability; multicast/sync only if product scope requires | 2026-09-13
45 | Typed patch/department/resource operational authority leases with fail-closed lifecycle fencing | 540 | Release Python + authority/schema/frontend/performance checks | 2/2 RT native CTest | Signed adaptation/authority receipts and externally witnessed Public Record | 2026-09-13
46 | Signed append-only adaptation/authority Public Record with external exact-hash witness attestations | 545 | Release Python + Public Record/schema/frontend/performance checks | 2/2 RT native CTest | Production-independent witness deployment/public-key transparency; governance/conformance bindings | 2026-09-13
47 | Signed technology conformance receipts bound to exact maturity evidence digests | 548 | Release Python + conformance/schema/frontend/performance checks | 2/2 RT native CTest | Independent witness option prioritized before community-governance expansion | 2026-09-14
48 | Strict independent-witness topology with unique IDs/domains/keyrings and signed clock-skew fencing | 555 | Release Python + witness reference/schema/frontend/performance checks | 2/2 RT native CTest; 3-process quorum drill passed | Real multi-host witness/recovery/failure-domain qualification | 2026-09-14
49 | Privacy-preserving community governance Public Record binding and evidence reconciliation | 559 | Release Python + governance/schema/frontend/performance checks | 2/2 RT native CTest | Real account-auth voting adapter; physical witness/LAN qualification | 2026-09-14
50 | Trusted auth-proxy community account sessions with generation-based revocation and session-only voting | 566 | Release Python + account-auth/schema/frontend/performance checks | 2/2 RT native CTest | Production IdP/LAN integration; remaining work requires external environments/platforms | 2026-09-14
51 | Linux external plugin adapter SHA-256 verification bound to exact inherited launch file descriptor | 568 | Release Python + plugin/schema/frontend/performance checks | 2/2 RT native CTest | Windows/macOS native launch binding; licensed real-plugin qualification | 2026-09-14
52 | Reviewed Focusrite Scarlett 4th Gen Windows x64 package metadata for exact USB identities | 569 | Release Python + driver-catalog/schema/frontend/performance checks | 2/2 RT native CTest (unchanged native source) | Windows/macOS endpoint evidence adapters; broader catalog re-review; physical qualification | 2026-09-14
53 | Offline driver-catalog review audit with expiry horizon and fail-closed stale/unreviewed/invalid reporting | 572 | Release Python + catalog-audit/schema/frontend/performance checks | 2/2 RT native CTest (unchanged native source) | Human vendor re-review; Windows/macOS endpoint evidence; physical qualification | 2026-09-14
54 | Real-Chromium rendered workflow and responsive reference acceptance with 390 px overflow fix | 573 | Release Python + Chromium/browser/schema/frontend/performance checks | 2/2 RT native CTest | Assistive-technology and deployed browser-to-LAN/TLS/IdP qualification | 2026-09-14
55 | Privacy-preserving Windows AudioEndpoint/signed-driver and macOS CoreAudio evidence adapters | 578 | Release Python + endpoint/driver/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Real Windows/macOS host execution; audio/device lifecycle and platform security adapters | 2026-09-14
56 | Persistence-grade WASAPI/CoreAudio/CoreMIDI identity-strength contract with weak-identity fail-closed reconnect rules | 584 | Release Python + identity/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Actual Windows/macOS enumeration, hotplug notifications, stream recovery and platform qualification | 2026-09-14
57 | Backend-agnostic audio stop plus exact-unique persistent MIDI rebind across native endpoint-ID churn | 600 | Release Python + device-lifecycle/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Real Windows/macOS enumeration/change notifications, physical audio/MIDI execution and qualification | 2026-09-14
58 | Backend-neutral physical-audio active-state and post-start identity fencing with explicit platform-preflight boundary | 604 | Release Python + audio-runtime/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | WASAPI/CoreAudio exact preflight/configuration and native stream adapters | 2026-09-14
59 | Transport-neutral bounded UPPF framing plus fail-closed Windows named-pipe ACL-validation contract | 610 | Release Python + local-IPC/session/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Real Windows DACL/listener/service integration and client/server execution | 2026-09-14
60 | Fail-closed Windows/macOS plugin launch attestation contract with no path-digest fallback | 614 | Release Python + plugin/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Actual Windows/macOS launch binders and licensed product qualification | 2026-09-14
61 | Installed isolated-rootfs Linux packaging qualifier with sysusers/tmpfiles, unit verification and state lifecycle checks | 616 | Release Python + package/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Real clean-host service boot/upgrade plus audio/MIDI/device permission qualification | 2026-09-14
62 | Real-Chromium accessibility-tree reference qualification for operator semantics | 618 | Release Python + Chromium AX-tree/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Actual screen-reader/switch/voice assistive-technology and deployed browser-network qualification | 2026-09-14
63 | Exact-build external qualification plan/result envelopes for all remaining environment-dependent gates | 621 | Release Python + qualification-bundle/schema/frontend/performance checks | 2/2 RT native CTest (native source unchanged) | Actual external witness/LAN/OS/AT/plugin/hardware execution and evidence review | 2026-09-14
64 | Authenticated exact-build external qualification evidence review with required artifact verification | 627 | Release Python + qualification-review/schema/frontend/performance checks | 2/2 RT native CTest | Actual external qualification execution and reviewer approval for remaining environment-dependent gates | 2026-09-14
65 | Exact-build external qualification intake/status aggregation with tamper-after-review detection | 631 | Release Python + qualification-status/schema/frontend/performance checks | 2/2 RT native CTest | Actual external evidence submission/review for the eight remaining qualification environments | 2026-09-14
66 | Protected explicit-SID Win32 CreateNamedPipeW listener for bounded authenticated UPPF | 638 | Release Python split full-suite + named-pipe/schema/frontend/performance checks | 2/2 RT native CTest | Actual Windows DACL inspection, unauthorized-client denial and service/client execution | 2026-09-14
67 | Pre-accept live kernel-DACL attestation for the protected Win32 UPPF named-pipe listener | 645 | Release Python split full-suite + Win32 ACL/schema/frontend/performance checks | 2/2 RT native CTest | Actual Windows GetSecurityInfo/client-denial/service execution | 2026-09-14
68 | Installed service-identity explicit device-permission qualifier for clean-host Linux hardware namespace evidence | 650 | Release Python split full-suite + device-permission/package/schema/frontend/performance checks | 2/2 RT native CTest | Real clean-host stageforge-user ALSA/MIDI/UWB device permission matrix | 2026-09-14
69 | Cross-platform GitHub Actions build/smoke harness with exact-engine platform evidence artifacts | 654 | Release Python + local Linux CI-smoke/schema/frontend/performance checks | 2/2 RT native CTest | Seed GitHub source; execute/review Windows and macOS hosted jobs; retain physical qualification separately | 2026-09-14
70 | GitHub-canonical hosted Windows kernel DACL, authorized UPPF roundtrip and unauthorized-client denial evidence | 654 | GitHub Platform Modules: Linux/Windows/macOS all green; Windows denial returned WinError 5 | Checkpoint 69 local 2/2 RT native CTest baseline retained; target module bytes unchanged | Production Windows service lifecycle/identity/restart integration; physical/platform hardware qualification remains separate | 2026-09-14
71 | Hosted Windows SCM LocalSystem service start/stop/restart with authenticated UPPF before and after restart | 654 | GitHub Platform Modules + generic CI green; downloaded Windows SCM evidence all intended lifecycle fields true | Checkpoint 69 local 2/2 RT native CTest baseline retained | Idle pending-accept stop cancellation remains; physical hardware remains separate | 2026-09-14
72 | Windows UPPF idle pending-accept shutdown and stale-handle-free SCM restart qualification | 654 | GitHub Platform Modules + generic CI green; idle STOP 0.266s and authenticated reconnect | Checkpoint 69 local 2/2 RT native CTest baseline retained | Windows IPC software row closed; remaining cross-platform work is audio/device/plugin plus external qualification | 2026-09-14
73 | GitHub-hosted Windows/macOS native verification-to-launch binders | 654 | Generic CI + StageForge Platform Modules green; Windows and Apple Silicon native-launch artifacts qualified | Checkpoint 69 local 2/2 RT native CTest baseline retained | Licensed plugin product matrices remain PLUG-035/036; physical hardware remains separate | 2026-09-14
74 | Native Windows MMDevice / macOS CoreAudio device monitor with explicit listener lifecycle | 2 | 1 native CTest per OS plus evidence executable; all 6 GitHub checks passed. No full-engine regression claim. | Hosted 25-cycle stop/restart, inactive/wrong-thread rejection and active destruction. Windows 0 endpoints; macOS 3. | DEV-033/034 remain In Progress. Event delivery, MIDI, persistent identity, engine integration and streaming remain open; no hardware qualification. | 2026-09-14

## Qualification Gates
Gate | State | Evidence Still Required | Backlog IDs | Claim Constraint
LAN security | Blocked | Real deployed TLS/proxy/certificate/IdP/firewall exercise plus physical independent-witness clock/network/failure-domain evidence | SEC-039, SEC-040 | Strict witness software/reference drill passes; no LAN-ready or physical-independence claim without deployed evidence
Persistent-fence recovery | Blocked | Real multi-host recovery through the strict 2-of-3 independent-witness topology, including one-witness loss | REC-033, REC-034 | Software/reference quorum is complete; no production recovery claim until independent hosts are exercised
Audio conversion | Blocked | Measured noise/distortion/phase/resampling quality on named physical interfaces | AUD-034 | Linux software execution is complete; no converter-quality or universal-hardware claim
Device hotplug | Blocked | Native event delivery, persistent identities, MIDI and engine reconciler integration; stream stop/reselection; named-device churn tests | DEV-033..DEV-035 | Checkpoint 74 native enumeration/listener lifecycle passed on both hosted OSes. No events observed; physical hotplug remains unqualified.
Live audio | Blocked | Named-hardware soak + licensed plugin qualification | LIVE-033, PLUG-033 | No stage-audio claim
Browser operations | Open | Actual screen-reader/keyboard assistive-technology exercise plus direct deployed browser-to-LAN/TLS/IdP qualification | UX-035, SEC-040 | Rendered/responsive and Chromium accessibility-tree references pass; no screen-reader or deployed browser-network claim
Linux packaging | Open | Real clean-host/VM boot and upgrade exercise plus stageforge-user runs of the installed device-permission verifier against actual ALSA/MIDI/UWB nodes | PKG-033, PKG-034 | Isolated-rootfs lifecycle and installed permission-verifier semantics pass; no real host/device qualification yet
Plugin coverage | Blocked | Licensed real-plugin compatibility matrices on Windows/macOS and remaining claimed OS/architectures | PLUG-035..PLUG-038 | Linux and hosted Windows/macOS launch-binding mechanisms are complete; no licensed-product compatibility claim
Cross-platform | Blocked | WASAPI/CoreAudio streaming, event delivery and engine integration; licensed platform plugin matrices | AUD-035/036, DEV-033/034, PLUG-035/036 | IPC and launch-binding software are closed. Native device monitor lifecycle passed; streaming, MIDI, licensed plugins and physical hardware remain unqualified.
Stage-qualified 6.0 | Deferred | Named hardware timing/soak/RF/failover/rehearsal evidence | HW-033..HW-037 | Release gate remains closed

## Definitions
Category | Value | Meaning
Status | Ready | Scoped, dependencies understood, can begin without inventing missing external evidence.
Status | Backlog | Valid remaining work but needs design/implementation before it is execution-ready.
Status | Blocked | Cannot be completed honestly without a missing environment, license, platform or external dependency.
Status | Deferred | Intentionally postponed qualification/equipment work; not complete.
Status | Done | Acceptance and verification evidence exist for this layer. Done software does not imply qualified hardware.
Type | Software | Code/protocol/configuration work that can be closed with deterministic software evidence.
Type | Qualification | Evidence work requiring a deployment, real browser, OS, device, plugin, RF environment or production-like rehearsal.
Type | Decision | Owner/governance choice that blocks downstream work.
Priority | P0 | Safety, authority, release or show-critical blocker.
Priority | P1 | Important capability/reliability work that should follow the current P0 seam.
Priority | P2 | Longer-horizon ecosystem/governance expansion.
Rule | Support claims | Only evidence from the relevant layer can close a claim. Inventory/discovery never substitutes for measured qualification.
Rule | Dates | No invented delivery dates. Sequence and gates are explicit; dates require real staffing/capacity.

## External Qualification Plan
StageForge External Qualification Plan
Plan sha256:6d6f16e34d55ead174f55bd7e2cb39d1ad225fb27c11845be24ccd6bb54e4fbd · Source sha256:64310cb7547ebf86b0b817ce7629a45a0564470469ce741872fccab65ecc8650 · Engine sha256:56cee8c0f3864b0eb897909c8152ea26d2a83a5f3c8beba4cb1728c19c48de59
Task | Backlog IDs | Required environment | Existing command | Required claims | Required artifacts | Result status | Review status | Evidence rule | Build binding
independent-witness | REC-033, REC-034, SEC-039 | three independently hosted witnesses plus primary/standby nodes | stageforge-witness-qualify.py | physicalIndependenceQualified twoOfThreeSurvivesOneWitnessLoss oneOfThreeDenied clockSkewWithinBound recoveredNodeRemainsStandbyDisarmed | qualification-report topology-inventory clock-evidence | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
lan-security | SEC-040 | deployed TLS reverse proxy, IdP/auth proxy and venue/control LAN firewall | stageforge-http-qualify.py | trustedCertificateQualified hostOriginBoundaryQualified idpIdentityQualified firewallIngressQualified controllerLoadQualified | qualification-report tls-certificate-chain firewall-policy | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
linux-packaging-host | PKG-033, PKG-034 | fresh Linux host or VM with representative audio/MIDI/device access | stageforge-package-qualify.py | cleanHostQualified serviceBootQualified upgradeStatePreserved hardwarePermissionsQualified uninstallPreservesState purgeRemovesState | qualification-report package-manifest service-evidence | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
windows-platform | AUD-035, DEV-033, PLUG-035 | supported Windows host with audio/MIDI hardware and plugin fixtures | Target-platform / manual harness | audioNegotiationQualified hotplugLifecycleQualified namedPipeDaclQualified pluginLaunchBindingQualified | qualification-report platform-observation security-evidence | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
macos-platform | AUD-036, DEV-034, PLUG-036 | supported macOS host with audio/MIDI hardware and plugin fixtures | Target-platform / manual harness | audioNegotiationQualified hotplugLifecycleQualified pluginLaunchBindingQualified | qualification-report platform-observation security-evidence | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
assistive-technology | UX-035 | real operator browser plus selected screen reader/keyboard AT stack | Target-platform / manual harness | keyboardWorkflowQualified screenReaderWorkflowQualified statusAnnouncementsQualified | qualification-report at-transcript | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
licensed-plugin-matrix | PLUG-033, PLUG-037, PLUG-038 | licensed real plugin fixtures on every claimed OS/architecture | Target-platform / manual harness | fixtureLicensesReviewed loadControlAudioRestartMatrixQualified delayCompensationQualified failureBypassQualified | qualification-report fixture-inventory compatibility-matrix | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
stage-hardware | AUD-034, DEV-035, LIVE-033, HW-033, HW-034, HW-035, HW-036, HW-037 | named production hardware and rehearsal topology | stageforge-qualify.py | latencySoakQualified audibleRecordingLoopQualified controllerTimingQualified rfClockQualified failoverTimingQualified | qualification-report hardware-inventory measurement-summary | External result required | Authenticated review required | Every required claim + artifact must verify before approval can be eligible for backlog review | Exact planId + source SHA-256 + native-engine SHA-256
Qualification rules
A result never closes a backlog item automatically. It must match this exact plan/build, use a hashed runner identity, keep physicalOutputsArmed=false, satisfy every required claim, and provide every required evidence artifact with verified SHA-256/size. An authorized reviewer then issues an authenticated approve/reject/needs-evidence envelope. Only an approval is eligible for backlog review; human/release review still decides whether the evidence is authentic and sufficient. This retained plan predates Checkpoint 74. Regenerate its exact source/engine binding before new qualification submissions; hosted module evidence does not update this plan.

## Qualification Intake
StageForge Qualification Intake Status
Exact plan sha256:6d6f16e34d55ead174f55bd7e2cb39d1ad225fb27c11845be24ccd6bb54e4fbd · pending 8 · approved 0 · invalid 0
Task | Backlog IDs | Status | Backlog-review eligible | Result SHA-256 | Reviewer hash | Reason | Next action
independent-witness | REC-033, REC-034, SEC-039 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
lan-security | SEC-040 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
linux-packaging-host | PKG-033, PKG-034 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
windows-platform | AUD-035, DEV-033, PLUG-035 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
macos-platform | AUD-036, DEV-034, PLUG-036 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
assistive-technology | UX-035 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
licensed-plugin-matrix | PLUG-033, PLUG-037, PLUG-038 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
stage-hardware | AUD-034, DEV-035, LIVE-033, HW-033, HW-034, HW-035, HW-036, HW-037 | pending | No |  |  |  | Run the external task and submit result.json + artifacts
Intake rule
Approved means the exact-build result, current evidence files, and authenticated review are internally consistent. It does not mark any backlog row Done. External evidence still needs release/owner judgment, and physicalOutputsArmed remains false throughout the qualification envelope.

## CI Platform Evidence
StageForge CI Platform Evidence
Checkpoint 74 · GitHub main f2fd64952c61f737e8b3dc60ee0afe86cd7de965 · native device monitor lifecycle passed on Windows/macOS
Environment | Runner | Build | Native tests | Platform smoke | Physical hardware | Evidence | Status
Linux module reference | ubuntu-24.04 | GitHub canonical platform modules | Passed | Import/hash-bound smoke passed | Not claimed | Checkpoint 73 workflow run 34870219024 | Passed hosted
Windows x64 | Windows Server 2025 | UPPF + SCM + native launch binder | Passed | DACL/denial/SCM plus Authenticode + stable file identity launch binder | Not claimed | launch artifact sha256:53e36074c526bd8909af0ddc695a17856d7d90efd1d50b8ea29b26d6dc300876 | Passed hosted / PLUG-034
macOS Apple Silicon | Darwin 23.6 arm64 | CoreAudio probe + native launch binder | Passed | CoreAudio evidence plus exact-byte private-copy codesign/CDHash launch binder | Not claimed | launch artifact sha256:527a6c92f6e277f3d5d6609fb42dabeb0d709e36755b8314b34487d1a9d60c92 | Passed hosted / PLUG-034
Windows device lifecycle | windows-latest / AMD64 | Test merge 32ef5c21fc9f583f2ae283a44abac97c05487368 | 1 CTest + evidence executable passed | 25 cycles; 0 devices; no defaults; 0 events; 0.304136 s | Not claimed | https://github.com/colinatwood/stageforge/actions/runs/34872231466 binary SHA-256: 18704f0b4ac6256ca346335f9cb8c1d163df049f98a21f0a4ad9fe0fdfc84a76 | Passed hosted; DEV-033 open
macOS device lifecycle | macos-14 / Darwin 23.6.0 arm64 | Test merge 32ef5c21fc9f583f2ae283a44abac97c05487368 | 1 CTest + evidence executable passed | 25 cycles; 3 devices; both defaults; 0 events; 0.25571 s | Not claimed | https://github.com/colinatwood/stageforge/actions/runs/34872231466 binary SHA-256: e7ef0c5ec71961eaf5add5359d8417c043b85c8c39761a04910d04ad3d06284a | Passed hosted; DEV-034 open
Claim boundary
Hosted CI proves the tested modules on the target OS, bound to source and executable hashes. Checkpoint 74 observed no notification events. Streaming, MIDI, physical hotplug, licensed products, timing and independent failure domains remain unqualified. Checkpoint 72 kernel/SCM evidence remains separate. No full-engine build or regression is claimed for Checkpoint 74.